## Sheet1
STEPS FOR RMEx/GUI INSTALL
STEP | Q rep | RESP PARTY/CLT | Due Date | Completed | Comment
For GUI Install
iSeries PTF's are Current
IP for iSeries
If PTF's are Current - make sure WAS 6.1 is installed
5733W61 WebSphere Application Server V6.1 for i5/OS
5733W61 WebSphere Application Server V6.1 Express
Install JAVA Options 6, 7 & 8
5722JV1-6 5722JV1-7 5722JV1-8
Ask clt to download Preliminary GUI doc (get location info)
Answers for Preliminary GUI doc from CLT to QTX
If Client needs to allow access from our location - give this IP to them 208.48.6.161/or set up site to site
GUI INSTALL - IF ALL questions have been answered and all items have been received then Geeva (Q2) can proceed with GUI install - they need 1-3 days
Move relevant libraries to iSeries for GUI |  |  |  |  | SCDATARM2 SCFIXRMX20 SCRMX20 ** NOW apart of the base!!
CLT has read RMEx 2.0 RLS doc -
Upgrade to RMX2 completed - CLT must UPGRADE to MOST recent version of RMEx
Move company 98 model over to clt 400 for DS and Events
Dynamic Scoring | PL/NZ | Kathy/Becky/Bill | 2011-06-15 | WIP | Nelson - there will be 8 jobs dedicated now…have added 1 for Dynamic scoring - installed June 16th evening…Nelson made changes and fixed items related to new file on June 17th---He moved the below libraries to the dot 6 machine. SCDATARM2 SCFIXRMX20 SCRMX20
PC server items to install for RMEx components:
Send Server Requirement doc to CLT/download?
New Server from Velocite - $3000 and $1500 to install pc components
Clt purchses New Server - $1500 we do/$500 for each item if we do not set up the server (if # of users exceeds 50, we recommend a second server) |  |  |  |  | Clt can puchase new/refurbished server and ship to us to do the install
IP for the Qserver
how are we to access the Qserver? Remote desktop? VNC?
Client Access needs to be installed on the new server |  |  |  |  | Clt access 5.4 and 6.1 both support 64 bit pcs…also, have client do a 'typical' install…that is all that is needed
Events
Clt needs to review Events DEMO - it is 33mins (location)
* Create Events Flow
* Create Smart Codes
* Setup Events
* Train & Communicate
Mobile Reports - (Smart phone reports) |  |  |  |  | clt has the software with instructions - Jamie will follow-up
PC files NEED to be installed!
Web Reports
PC files NEED to be installed!
Emailing Letters
PC files NEED to be installed!
EPP-real time CC payments
PC files NEED to be installed!
CBOSS - real time CC payments
PC files NEED to be installed!
CCMS - Call & Screen recording
1. Properly install Windows7 or Windows XP (Service pack 3 or higher is recommended)
2. Network connectivity between I-Tel Dialer Recording folder and Agent-PCs
3. Network connectivity between AS400 machine and Agent-PCs
4. Network connectivity between Manager PC and the Agent-PCs
5. Network connectivity between File Server (used to store audio merged video files) and the Agent-PCs
6. Network connectivity between File Server and the Manager-PC
7. PC needs to be free of any other third party software that can obstruct the socket connections
CCMS - PC files NEED to be installed on various PC's - Agents & Mgr!
Dashboard--
Dashboard - PC files NEED to be installed!
**need to have IBM Clt Access ODBC drivers at minimum for Dashboard
CLT needs to provide a list of options and # of users for each SENT to Q |  |  |  |  | This info will dictate the amount of memory and disk for the server
The minimum configuration for all components is as follows:
1. Intel Xenon processor – 2.0 Ghz
2. Windows 2008 server – 64 bit
3. 6 Gb RAM
4. Raid 1
5. 2 x 1TB Hard Drives
6. Redundant power supply
7. 1 x 1 Gb Network card
RMEx items that don’t need PC files installed
Dynamic Scoring
* Create 40 Smart Codes
* Create 12 Desc.Codes
* Setup DS
* Clear files 1)if restarting DS, 2) |  |  |  |  | SCDACTUP & SCDISCOA
* Run Update program when? |  |  |  |  | DACFIRST